## Sheet1
| November |  | December |  |  | 🎅 | January |  |  |  |  | February |  |  |  | March
| 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 6 | 13 | 20 | 27
Background
Literature review
Thesis Problem definition
Simulation Environment
Evaluate NPFG for MC/FW in Windy Wings
Evaluate Jerk induced by NPFG (MC)
Benchmark against NPFG | [7 empty] | x | x | x | x | x
Include Wind dynamics in Simulation | [9 empty] | x | x | x
Benchmark new formulation in Wind | [9 empty] | x | x | x
Theoretical Formulation
Formulate new ref vector for multicopter | [9 empty] | x | x | x
Apply new formulation for VTOL | [7 empty] | x | x | x | x | x
Consider wind into guidance | [8 empty] | x | x | x | x
Testing
Implement new guidance in PX4 | [9 empty] | x | x | x
Evaluate new guidance in SITL | [9 empty] | x | x | x
Evaluate new formulation on real MC | [10 empty] | x | x
Evaluate new formulation on real VTOL | [11 empty] | x
Documentation
Weekly report (due Sunday, 3pm CET) | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
Latex lemplate familiarity
Intermediate presentation | [7 empty] | 9.01
Prepare final presentation | [16 empty] | 13.03
Final report writing | [18 empty] | 27.03
x: Didn't do
|  |  |  | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5